## MVP_Economic_estimation
Step	TimeEstimation [h]	Position	Unitary Price [USD]	Price [USD]	Reference Links
Simple Trapdoor 1 and 2	4	Junior Pyhton Developer	15	60	https://docs.python.org/3/library/hashlib.html
Paid processing	80	Junior Pyhton Developer	15	1200	https://github.com/topics/bitcoin-payment-gateway / https://github.com/topics/payment-gateway?l=python&o=desc&s=updated / https://github.com/bitcartcc/bitcart / https://github.com/bitpay/bitcore#bitcore / https://ofek.dev/bit/
Timing consuming procedure using Argon2	20	Junior Pyhton Developer	15	300	https://github.com/P-H-C/phc-winner-argon2 / https://github.com/ultrahorizon/pyargon2
First half integration and some tests	16	Junior Pyhton Developer	15	240	Based on personal experience with other Python projects developed
Alice's Intervention	20	Junior Pyhton Developer	15	300	Based on first prototype implementation
Second half integration and final tests	16	Junior Pyhton Developer	15	240	Based on personal experience with other Python projects developed
FrontEnd	100	Python Front End Developer	20	2000	Sugestion: Kivy framework https://kivy.org/ / Time estimation from consulting a Software Front end Developer of the company ExamRoom.Ai / https://examroom.ai/
Project Management	32	Project Manager	0	0	Suggestion, follow the steps of Agile Methodology. Once daily (each day) and one week sprint. / The daily may take about 30 minutes and the Sprint Review and Sprint Grooming about 1h30m (at average)
R&D	320	Researcher	0	0
AI_integration (estimated 120 h left for after MVP)	0	Python Machine Learning Engineer	75	0
Total	608	-	-	4340

			non economic estimation	51440
			reduction rate	11.852534562212

## MPV_TIme_estimation
Step	Time Estimation [h]	Position	Unitary Price [USD]	Price [USD]	Reference Links
Simple Trapdoor 1 and 2	4	Junior Pyhton Developer	40	160	https://docs.python.org/3/library/hashlib.html
Paid processing	80	Junior Pyhton Developer	40	3200	https://github.com/topics/bitcoin-payment-gateway / https://github.com/topics/payment-gateway?l=python&o=desc&s=updated / https://github.com/bitcartcc/bitcart / https://github.com/bitpay/bitcore#bitcore / https://ofek.dev/bit/
Timing consuming procedure using Argon2	20	Junior Pyhton Developer	40	800	https://github.com/P-H-C/phc-winner-argon2 / https://github.com/ultrahorizon/pyargon2
First half integration and some tests	16	Junior Pyhton Developer	40	640	Based on personal experience with other Python projects developed
Alice's Intervention	20	Junior Pyhton Developer	40	800	Based on first prototype implementation
Second half integration and final tests	16	Junior Pyhton Developer	40	640	Based on personal experience with other Python projects developed
Memorization Assistant	250	Junior Pyhton Developer	40	10000
Front-End	100	Python Front End Developer	38	3800	Suggestion: Kivy framework https://kivy.org/ / Time estimation from consulting a Software Front end Developer of the company ExamRoom.Ai / https://examroom.ai/
Project Management	32	Project Manager	100	3200	Suggestion, follow the steps of Agile Methodology. Once daily (each day) and one week sprint. / The daily may take about 30 minutes and the Sprint Review and Sprint Grooming about 1h30m (at average)
R&D	240	Researcher	80	19200
AI_integration	120	Python Machine Learning Engineer	75	9000

Total	898	-	-	51440

## Price_Estimation
Position	Price Reference
Python Junior Developer	https://www.glassdoor.com/Salaries/junior-python-developer-salary-SRCH_KO0,23.htm
Front End Developer	https://www.glassdoor.com/Salaries/front-end-web-developer-salary-SRCH_KO0,23.htm
Python Project Manager	https://www.glassdoor.com/Job/project-manager-python-jobs-SRCH_KO0,22.htm / https://www.payscale.com/research/US/Job=Project_Manager%2C_Software_Development/Salary/2ca2576b/Python
Python Machine Learning Engineer	https://www.glassdoor.com/Salaries/python-ml-engineer-salary-SRCH_KO0,18.htm